## IBHE Checklist
Packet Section | Estimated Timeline | Checklist Item | Assigned | Status | Date Completed | Notes
1 | 4 month prior to launch | Form Campus Committee | Survey Coordinator |  |  | Identify a survey coordinator, communications member, and Title IX or Confidential Resource Member.
1 | 4 month prior to launch | Submit Budget to Leadership | Committee
1 | Completed in Packet | Optional: NFHS Determination Application | Survey Coordinator | Complete |  | Since this is for Program Improvement and legislative requirement, IRB should not be needed as this is not deemed as research, however you may elect to submit a Non Human Subject Research Determination Request to your IRB
1 | 3 months prior to launch | Determine incentives/prizes and purchase | Survey Coordinator
1 | 3 months prior to launch | Optional: Create shorturl's and QR Code for marketing | Communications
1 | 3 months prior to launch | Optional: Create email for survey | Survey Coordinator | Example Provided |  | Example; sexualmisconductsurvey@insitution.edu
1 | 3 months prior to launch | Optional: Create a webpage with FAQ's | Communications | Example Provided |  | Example: https://sexualmisconductsurvey.illinois.edu/
2 | 3 months prior to launch | Finalize language for campus resources to be added to the survey | Committee
2 | Completed in Packet | Upload Survey into Qualtrics | Survey Coordinator |  |  | Survey has been created for you in the IBHE Packet
2 | 1 month prior to launch | Edit insitution specific questions | Survey Coordinator |  |  | See "Survey Questions that are Modifiable"
2 | 1 month prior to launch | Review Qualtrics Survey Settings | Survey Coordinator |  |  | See "Qualtrics Survey Settings"
2 | 1 month prior to launch | Edit and upload all Custom Messages | Survey Coordinator |  |  | See "Qualtrics Custom Messages"
2 | 1 month prior to launch | Create an form for students to enter for incentives | Survey Coordinator
2 | 1 month prior to launch | Survey Testing | Committee | Instructions Provided |  | Ask committee to test the survey, see Survey Testing Template
2 | 1 month prior to launch | Optional: Test Survey Accessibility | Campus Accessibility Contact | Template Provided |  | The survey provided has been tested for accessibility, but you may choose to do an additional review
2 | 1 month prior to launch | Set up No Spam Rule | Survey Coordinator |  |  | Depending how emails are distributed, contact your IT folks to ensure it not stopped by SPAN Filters
2 | 3 weeks prior to launch | Work with Insitutional Research to ensure accurate participant list | Survey Coordinator |  |  | All current students and any student who was enrolled in the last year
2 | 1 week prior to launch | Email Communication Plan to Service Providers | Survey Coordinator |  |  | Email staff with direct support for survivors with information about emails
2 | Launch date | Launch Survey | Survey Coordinator
2 | 9 days after launch | Review demographic responses | Survey Coordinator |  |  | If there is a demographic population that is under-represented compared to campus population, develop specific outreach
3 | Completed in Packet | Create Logo and Marketing Materials | Communications | Template Provided
3 | 1 month prior to launch | Finalize Student Communication Emails/Reminders, obtain approval | Communications | Template Provided |  | Examples are provided in the Marketing and Communications folder
3 | 1 month prior to launch | Socialization to Campus leadership - Information PPT | Communications | Template Provided
3 | 1 week before launch | Distribute Digital Signage or Physical Flyers on Campus | Communications | Template Provided
3 | 1 month prior to launch | Award Incentives | Survey Coordinator
3 | Launch date | Survey Invite: Communication #1 | Communications | Template Provided |  | Survey must stay open 5 weeks. (see IBHE General Guidance - April 1, 2024)
3 | 5 days after launch | Survey Invite: Communication #2 | Communications | Template Provided
3 | 2 weeks after launch | Survey Invite: Communication #3 - Targeted Populations | Communications | Template Provided
3 | 4-5 weeks after launch | Survey Invite: Final Communication #4 | Communications | Template Provided
3 | 5-6 weeks after launch | Advertised Close Date | Survey Coordinator
3 | 5-6 weeks after launch | Close Survey | Survey Coordinator |  |  | We often leave a survey open for a few days after the advertised close date
4 | After Close | Remove participants who stopped before Q33 | Survey Coordinator |  |  | (see IBHE General Guidance - April 1, 2024)
4 | After Close | Additional Data Cleaning | Survey Coordinator | Instructions Provided
4 | 1 month after close | Complete IBHE Reporting Template | Survey Coordinator | Template Provided
4 | 1 month after close | Create a report for posting on insitution website | Survey Coordinator | Template Provided
4 | 2 months after close | Optional: Data Prep for Additional Analysis | Survey Coordinator | Instructions Provided |  | SPSS Syntax File: Syntax_PrepData_2025_IBHE
4 | 4 month after launch | Optional: Create a presentation for internal use | Survey Coordinator | Template Provided |  | PPT File provied and accompanying SPSS Syntax
4 | 4 months after luanch | Optional: Create a 1-page summary for internal use | Survey Coordinator | Template Provided |  | PPT File provied and accompanying SPSS Syntax